GNSO Council Restructuring Implementation Plan Strawman

Potential Outline/Table of Contents of Implementation Plan/Report:

- Introduction and Summary (including explanation that restructuring implementation is separate (but parallel) track from PPSC and OSC efforts)

- Structure of Implementation/Transition Effort

- Key Process and Implementation Decisions/Issues

- Calendar of Timelines/Deadlines for Transition to/Implementation of Restructured GNSO Council

Key Process and Implementation Decisions to Effectuate Transition to Restructured GNSO Council (beyond first four bullets - not in any priority order):

- Determine form, structure and composition of implementation/transition oversight (drafting team, task force, working group, council subcommittee, etc.)

- Determine working method and decision-making mechanism of that TBD structure (consensus, majority, etc.)

- Develop and confirm inventory of key process, transition and implementation decisions.

- Develop goals, milestones and timetable for decisions

- Establish form and frequency of update/reporting mechanism to Board.

- Chair Election for Restructured GNSO Council – determine appropriate timing (elect before, after or concurrent with new Council being seated); as directed by Board, establish voting process beyond the first ballot.

- Identification and development of any additional voting thresholds or categories that may be needed (as directed by Board).

- Apportionment mechanism for Nominating Committee Appointees – how are NCAs assigned to each house and the council-level position?

- NCA criteria – supply guidance to Nominating Committee regarding qualification/factors to consider for future appointees?

- Consider new and or continuing roles of liaison and observers from ALAC, GAC and ccNSO.

- Consider application of geographic diversity considerations to selection of Council members.

- Consider implications for travel funding

- Determine/define appropriate Council interface, if any, with stakeholder groups during transition (e.g., coordination, best practices or status reports).

- Determine/define Council interface, if any, with constituency groups during transition (e.g., coordination, best practices or status reports).

- Determine/define selection/seating/timing process for new council members in June 2009 and coordinate with constituencies/stakeholder groups as appropriate – need for clear understanding of whether new election/selections are necessary/appropriate?

- Staggering of Council member terms to ensure smooth transitions in future?

- Application of term limits - if approved by the Board.

- Consider impact of June 2009 seating timetable on existing Council member terms and immediately subsequent Councilor terms?

- Vice-Chair Selection process for each voting house – timing and mechanisms TBD by each voting house (potential post-June decision)

Please identify any others for discussion …..

Potential Calendar of Timelines/Deadlines for Transition to/Implementation of Restructured GNSO Council (does not include implementation of any other “improvements” matters being addressed by PPSC or OSC):

December 2008:

- GNSO Council restructuring implementation plan submitted in advance of the 11 December 2008 Board Meeting;

- Begin by-law mandated GNSO Council Chair Election process for existing Council (dates taken from GNSO Secretariat draft timetable):

Call for nominations for GNSO Council Chair
Monday 1 December 2008 to Monday 15 December 2008 (2 weeks)

Possible interviews with the candidates
Tuesday 16 December candidate slate announced

Proposed period to interview candidates
16 December - 23 December 2008

January 2009:

Voting for GNSO Council chair
Monday 5 January to 14 January 2009

Thursday 15 January 2009 announce the result of the GNSO Council Chair

Call for nominations for GNSO Council Vice Chair
Thursday 15 January 2009 to Thursday 22 January 2009

29 January 2009 GNSO Council meeting
Confirmation of the GNSO Council Chair
Vote for GNSO Council Vice Chair

30 January 2009 end of term for current Chair and Vice Chair

February 2009:

- Early February 2009 - Existing GNSO Constituencies submit confirmation documents to the Board for review in advance of the February 2009 Board Meeting;

March 2009:

- March 2009 – New GNSO Stakeholder Groups submit formal plans for Board approval for consideration at the 6 March ICANN Mexico City Board meeting;

- Board decision regarding GNSO constituency confirmations?

April 2009:

- April 2009 – Board decisions regarding Stakeholder Group plans?

- 30 April – Deadline for confirming decisions on all outstanding transition issues for restructured Council

May 2009:

- May 2009 – Board-approved Stakeholder Groups appoint/select/determine Council representatives

- New Council Chair election process confirmed

June 2009:

- June 2009 - Newly-structured GNSO Council is seated at the June 2009 GNSO Council meeting in Sydney, Australia.