## Sheet1
PDP Milestone | WHOIS Task force 1: Restricting access to WHOIS data for marketing purposes |  |  |  | WHOIS task force 2: Review of data collected and displayed |  |  |  | WHOIS task force 3: Improving Accuracy of collected data |  |  |  | Approval process for gtld service changes
| TF milestone | PDP target date | Revised Target Date | Actual date | TF milestone | PDP target date | Revised Target Date | Actual date | TF milestone | PDP target date | Revised Target Date | Actual date | Council milestone | PDP target date | Revised Target Date | Actual date
Issue raised |  |  |  | 2003-03-25 |  |  |  | 2003-03-25 |  |  |  | 2003-03-25 |  |  |  | 2003-10-03
Issues report requested by Council |  |  |  | 2003-03-25 |  |  |  | 2003-03-25 |  |  |  | 2003-03-25 |  |  |  | 2003-10-16
Publish Issue Report |  | 2003-04-10 |  | 2003-05-13 |  | 2003-04-10 |  | 2003-05-13 |  | 2003-04-10 |  | 2003-05-13 |  | 2003-11-01 |  | 2003-11-19
Council to meet to discuss Issue Report |  | 2003-04-25 | 2003-05-28 | 2003-05-22 |  | 2003-04-25 | 2003-05-28 | 2003-05-22 |  | 2003-04-25 | 2003-05-28 | 2003-05-22 |  | 2003-11-16 | 2003-12-04 | 2003-11-20
Council to initiate PDP |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-11-16 | 2003-12-04 | 2003-12-02
Council to decide on whether to convene a task force |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-04-25 | 2003-05-28 | 2003-10-29 |  | 2003-11-16 |  | 2003-12-02
Council to develop terms of reference |  | 2003-05-05 | 2003-11-08 | 2003-10-29 |  | 2003-05-05 | 2003-11-08 | 2003-10-29 |  | 2003-05-05 | 2003-11-08 | 2003-10-29 |  | 2003-11-26 |  | 2003-12-02
Constituencies to appoint reps to task force |  | 2003-05-05 | 2003-11-08 | 2003-11-17 |  | 2003-05-05 | 2003-11-08 | 2003-11-17 |  | 2003-05-05 | 2003-11-08 | 2003-11-17 |  | 2003-11-26
Council to approve timeline |  | 2003-05-05 | 2003-11-08 |  |  | 2003-05-05 | 2003-11-08 |  |  | 2003-05-05 | 2003-11-08 |  |  | 2003-11-26
Commence first 20 day public comment period |  | 2003-04-25 | 2003-10-29 | 2003-11-07 |  | 2003-04-25 | 2003-10-29 | 2003-11-07 |  | 2003-04-25 | 2003-10-29 | 2003-11-07 |  | 2003-11-16 |  | 2003-12-05
Conclude first 20 day public comment period |  | 2003-05-15 | 2003-11-18 | 2003-11-28 |  | 2003-05-15 | 2003-11-18 | 2003-11-28 |  | 2003-05-15 | 2003-11-18 | 2003-11-28 |  | 2003-12-06 |  | 2003-12-28
Initial meeting of task force |  | 2003-05-10 | 2003-11-13 | 2003-12-02 |  | 2003-05-10 | 2003-11-13 | 2003-12-01 |  | 2003-05-10 | 2003-11-13 | 2003-12-01
Appointment of task force chair |  | 2003-05-10 | 2003-11-13 | 2003-12-02 |  | 2003-05-10 | 2003-11-13 | 2003-12-01 |  | 2003-05-10 | 2003-11-13 | 2003-12-01
| Dissemination of past WHOIS material |  | 2003-12-23 | 2004-01-05
| Identification of non-marketing groups |  | 2003-12-23
| 1st draft of notice to non-marketing groups |  | 2004-01-05
| 1st draft of needs and justification chart |  | 2004-01-06
| Send out notice to non-marketing groups |  | 2004-01-12
| Conclude comment period from non-marketing groups |  | 2004-01-26
Submission of constituency statements |  | 2003-06-01 | 2004-02-01 |  |  | 2003-06-01 | 2004-02-23 |  |  | 2003-06-01 | 2004-02-23 |  | 2004-01-12 | 2003-12-21
| Document changes needed to registry/registrar agreements |  | 2004-02-09
Distribute Preliminary Task Force Report |  | 2003-06-06 |  |  |  | 2003-06-06 | 2004-03-26 |  |  | 2003-06-06
Task force to meet to discuss Preliminary Task Force Report |  | 2003-06-11 |  |  |  | 2003-06-11 |  |  |  | 2003-06-11
Publish Task Force Report (Initial Report) |  | 2003-06-16 | 2004-03-01 |  |  | 2003-06-16 |  |  |  | 2003-06-16 | 2004-03-16 |  |  | 2004-01-06
| ICANN meeting in Rome |  | 2004-03-02 |  |  |  | 2004-03-02 |  |  |  | 2004-03-02
Commence second 20 day public comment period |  | 2003-06-16 |  |  |  | 2003-06-16 |  |  |  | 2003-06-16 | 2004-03-17 |  |  | 2004-01-06
Conclude second 20 day public comment period |  | 2003-07-06 |  |  |  | 2003-07-06 |  |  |  | 2003-07-06 | 2004-04-06 |  |  | 2004-01-26
Publish Final Report |  | 2003-07-16 |  |  |  | 2003-07-16 |  |  |  | 2003-07-16 | 2004-04-20 |  |  | 2004-02-06
Council to meet to discuss Final Report |  | 2003-07-26 |  |  |  | 2003-07-26 |  |  |  | 2003-07-26 |  |  |  | 2004-02-16
Council to vote on accepting the policy recommendations |  | 2003-07-26 |  |  |  | 2003-07-26 |  |  |  | 2003-07-26 |  |  |  | 2004-02-16
Publish Board report |  | 2003-08-01 |  |  |  | 2003-08-01 |  |  |  | 2003-08-01 |  |  |  | 2004-02-21